## Sheet1
Project Crashing Example
Description:
The project crashing problem seeks to minimise the total cost of crashing (reducing) task durations and meet an earlier target completion time while being limited by available resources and task dependencies. Note that if the solver cannot find a feasible solution, this means that the project cannot be crashed to the target time but may still be crashed.
Example context:
This model seeks to minimise the cost of crashing the project and reduce the project's completion time from 25 months to 21 months by allocating resources efficiently, and determining which tasks to crash and by how much.
Model:
| Task C | Task D | Task E | Task F | Node 0 | Node 1 | Node 2 | Node 3 | Node 4 | Node 5 | Node 6 | Node 7 | VALUE |  | RHS
Solution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Minimise | 30000 | 60000 | 12000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subject to | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bound C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <= | 2
Bound D | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <= | 4
Bound E | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <= | 2
Bound F | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <= | 1
Start | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | = | 0
Current completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | <= | 25
Node 0 to 1 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | >= | 2
Node 1 to 2 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | >= | 4
Node 2 to 3 | 1 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | >= | 5
Node 2 to 4 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | >= | 8
Node 3 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | >= | 0
Node 4 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | >= | 0
Node 3 to 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | >= | 9
Node 4 to 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | >= | 8
Node 5 to 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | >= | 6
Node 6 to 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | >= | 3
Target completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | = | 21
Cost of crashing | 0
min
≤
=
≤
≥
=